## Villa 1 to 79
Report - details of posession.
Project Name: |  | Nilgiri Estates | Prepared By: | Madhusudan |  |  | Date: |  | 2018-06-18
Block / Phase: |  | Villa nos 1 to 79.
Villa / Flat No. | No. of bedrooms | Customer name | Sate III QC report date | Stage IV completed? (Yes / No) | Possession letter issued by CR? (Yes / No) | Hanover date mentioned in posession letter. | Actual date of posession given. | MMC due from - month/year | Villa occupied by owner / tenant? | Remarks (If possession not given provide details of pending work. If possession was given after due date provide reasons for delay)
1 | 2BHK | Jhansi Rani Valavala | 2018-06-07 |  | Yes | 2018-06-30 | 2018-07-30 | 2022-10-01
2 | 3BHK | Ramesh Donepudi | 2018-05-15
3 | 4BHK | Ponugoti Sukanya | 2018-04-12
4 |  | Rajashekar Vadluri / Shoba Rani
5 |  | BSRC Murthy/B.Sarala |  | yes | yes | 2017-10-31 |  |  | yes
6 |  | Balaji Raghavendran/B.Vidya
7 |  | Mr.Lakshminarayanan.R |  |  | yes | 2018-03-03 |  |  | yes
8 |  | Dr.Manoj M.Khivsare&Dev.M.K
9 |  | Yadagiri Sriram Jogula | 2017-03-17
10 |  | Dillip Kumar Routrey | 2017-05-23
11 |  | Mrs.Susmi Routray/Rajib Kumar Routray | 2017-06-17
12 |  | Hari Kishan T.R
13 |  | Ranga Srinivas
14 |  | S.A.Srinivasa Rao
15 |  | Omkar Mudigonda |  |  | yes | 2018-04-20
16 |  | G.Ram Mourya / G.Vaishnav | 2017-06-05 |  | yes | 2017-11-27
17 |  | Sneha Jagadeep | 2017-06-17 | Yes | yes | 2018-01-18 |  |  | yes
18 |  | MIR Kazim Ali Khan | 2017-06-16 | yes | yes | 2018-02-05
19 |  | Gattu Murali |  |  | yes | 2018-03-03
20 |  | Pradeepthi Bhimavarapu
21 |  | S.M.Raghu Ram |  |  | yes | 2018-04-30
22 |  | Pallavi N
23 |  | T.C.Sunil/P.Deepika | 2017-06-27 | yes | yes | 2017-12-12 |  |  | yes
24 |  | Dr.Juliet Josephin.J /Dr. G.Madhusudhan Rao
25 |  | J.Rajendra Prasad | 2017-07-17
26 |  | Vijay Kumar.K
27 |  | Swathi Dinesh Jaiswal | 2018-05-11 | yes | yes | 2018-06-09 |  |  | yes
28 |  | Sreenivas Meenakshi Sundaram | 2017-06-27 |  | yes | 2018-06-08
29 |  | Vuggini Ravindar | 2017-06-27 | YES | yes | 2017-11-10
30 |  | Raja Suman Kumar Thogaru | 2017-06-27 |  | yes | 2018-06-07
31 |  | M.Aruna/M.Jaya Prakash | 2017-06-27 | YES | yes | 2017-08-31
32 |  | Adapa Vidya Sagar | 2017-06-24 | YES | yes | 2018-01-12 |  |  | yes
33 |  | Raja Vijay Kumar Thogaru | 2017-09-27 |  | yes | 2018-06-07
34 |  | Sandeep Pulluri (Mort)
35 |  | Pendru Sugunakar Reddy (Mortgaged)
36 |  | Surinder Reddy Surkanthi (Mortgaged) |  |  | yes | 2018-02-28
37 |  | Bala Surya Vijay Kumar Beesetty (Mortgaged)
38 |  | V.Srinivasa Rao
39 |  | Dornala Venkata Sridhar Murthy
40 |  | K.Roopesh
41 |  | DVN Prasad
42 |  | Harshal M Ghodgaonkar
43 |  | Shagufta Yasmin
44 |  | M.Chandrika/M.Suresh
45 |  | Guru Prasad Rao Palanki | 2017-07-11 |  | yes | 2017-11-21 |  |  | yes
46 |  | Nakkina Annapoorna/Alle Vijay Kumar |  |  | yes | 2018-01-02
47 |  | Priyanka Kose |  |  | yes | 2018-02-10
48 |  | Rudroju Anjaneyulu/R.Vimala
49 |  | Anwar Akhtar/Ashna Abdin
50 |  | Boda Sandeep Kumar
51 |  | Vijaya Lakshmi ramakrishna Ballal | 2017-07-31 |  | yes | 2018-01-12 |  |  | yes
52 |  | V. S. M. Vishnu | 2017-03-17 |  | yes | 2018-02-05
53 |  | Mandala Venugopal Reddy | 2017-06-28 |  | yes | 2018-05-31 |  |  | yes
54 |  | Vaddadi Ravi Kiran | 2017-08-08
55 |  | Pindi Ram Narayana | 2017-07-03 |  |  | 2018-05-05
56 |  | T.Sridhar | 2017-07-11 |  | yes | 2018-05-10
57 |  | Gopi ChandarThakkallapelli | 2017-08-12 |  | yes | 2017-11-21 |  |  | yes
58 |  | Srinivas Rao.K | 2017-06-28 |  | yes | 2018-02-05 |  |  | yes
59 |  | Nagam Devi Vara Prasad | 2017-09-13
60 |  | Vooradi Ram - Sagar | 2017-06-05
61 |  | V.Ramakrishna | 2017-06-05
62 |  | Satish Kumar Kankati | 2017-06-05 |  | yes | 2018-02-28 |  |  | yes
63 |  | Rajesh Kumar Mididoddi | 2017-05-12 |  |  | 2018-02-28
64 |  | D.Vignana Tejaswi | 2017-05-11 |  | yes | 2018-05-10
65 |  | Pendem Rakesh/Pendem Vanisri | 2017-06-23
66 |  | Santosh Mandapuram
67 |  | M.Shobha | 2018-04-16 |  | yes | 2018-06-11
68 |  | Bellamkonda Sireesha | 2017-07-17 |  | yes | 2017-11-21 |  |  | yes
69 |  | Ekloveya Pratap Dwivedi & Ranjana Tiwari | 2017-07-17 |  | yes | 2017-09-20
70 |  | D.V.A.H.G.Swaroop
71 |  | Mr.CH.Srirama Sastry
72 |  | Kanu Kolanu Sree KRishna Rao | 2017-09-19 | yes | yes | 2018-04-30
73 |  | CH.Sujatha | 2017-03-17
74 |  | Vinnakota Aaditya | 2018-05-16
75 |  | Vinnakota Venkata Venu Madhav
76 |  | Vinnakota Sridhar/V.Shanthi
77 |  | Dr.Sreedevi
78 |  | Vasudha Sirasanagandla | 2017-09-09 |  | yes | 2017-12-31 |  |  | yes
79 |  | Dr.A.Ramachandran | 2018-05-07 |  | yes | 2018-01-03 |  |  | yes
80
81
82
83
84
85
Note: | Make separate sheet for each block / phase.