## KNM
Prepared by: | Kavitha
Report Date | 2022-03-10
Site | MRGV
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
95039 | 21-01-2022 | Laptop bags | Online purchase
95063 | 2022-11-02 | Callisto AC CTY00034 tiles | Req. with MD
95068 | 25-02-2022 | Wifi router | Online purchase
95069 | 25-02-2022 | Emery paper | Cancelled by site
List of requisitions Where PO/WO is prepared and items have not received at site
Follow up with suppleir
95032 | 17-01-2022 | UPVC Windows | Contact supplier
95033 | 17-01-2022 | UPVC Sliding doors | Contact supplier
95061 | 2022-02-09 | Electrical conductives | Partly delivered from ssllp
95066 | 22-02-2022 | Drilling machine | Contact supplier