## KNM
Prepared by: | Kavitha
Report Date | 18-03-2022
Site | Aedis Developers LLP
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
List of requisitions Where PO/WO is prepared and items have not received at site
100578 | 19-01-2022 | Aerocan bricks | Contact Supplier
100587 | 14-02-2022 | Matress | Contact Supplier