## GVRC
Prepared by: |  | P.Prabhakar
Report Date |  | 2022-03-12
Site |  | ,.
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
164173 | 2021-11-22 | FRP Manholes | Cancell this requisition and send a new requisition
164402 | 2022-01-10 | Brethe analasys | Cancelled by MD
164436 | 2022-01-18 | 1 hp pump, with suitable pipe, diesel hand pump | Requisition sent for mds approval
164568 | 2022-02-16 | Hand drayer machione, Bin, Tissue paper | PO to be issue
164599 | 2022-02-21 | Cutting wheels, tester, cutting plair | PO to be issue
164612 | 2022-02-23 | MS Ladder | Estimate to be prepare
164632 | 2022-02-24 | Horizantal centrifugal motor guard | Requisition sent for mds approval
164636 | 2022-02-26 | Foam board5 mm | Cancelled by MD
164638 | 2022-02-26 | Self screws | Cancelled by MD
164640 | 2022-02-26 | Office table, revolving low storage | PO 86344
164648 | 2022-03-03 | Gun grey paint | PO 86088
164649 | 2022-03-03 | Camera memory cartd | Online purchase
164640 | 2022-03-03 | Solar panel | Quotes to be received
164655 | 2022-03-03 | Asian exeterior primer | PO 86214
164664 | 2022-03-05 | Digital water meter, normal meter | Hold by MD
164665 | 2022-02-05 | Low storage | PO 86340
164666 | 2022-03-05 | STP Water proofing | Requisition not found in email send it again
164668 | 2022-03-05 | Epoxy coat water proofing | Requisition not found in email send it again
164669 | 2022-03-05 | Water proofing for sumps | Requisition not found in email send it again
164670 | 2022-03-05 | Full thread waste coupling | PO 86335
164674 | 2022-03-07 | Coffee powder, lemon powder | PO to be issue
164679 | 2022-03-07 | Tenax | Locally purchased by Raghu and sent you, close this requisition
164680 | 2022-03-07 | Wire brushes | Locally purchased by Raghu and sent you, close this requisition
164685 | 2022-03-08 | Single bed, dining table, 4 chairs | PO 86222, 86455
164688 | 2022-03-08 | L Angle | PO 86309
164695 | 2022-03-09 | 3.5 Core straight cable jointing kit | Estimate to be prepare
List of requisitions Where PO/WO is prepared and items have not received at site
163704 | 2021-08-07 | ACP cladding | Work under progress
164011 | 2021-12-08 | Busduct material | Work under progress
164260 | 2021-12-08 | Goods lift | Work under progress
164366 | 2021-12-30 | GI Piping wrapping material | Delivery next week
164448 | 2022-01-20 | Steel grey granite | Co ordinate with Leela krishna granite supplier fro delivery
164457 | 2022-01-22 | SS Railing | Co ordinate with Leela krishna granite supplier fro delivery
164519 | 2022-02-07 | Sand stone light grey | Deliverd
164534 | 2022-02-11 | Electrical gloves | Co ordinate with Leela krishna granite supplier fro delivery
164541 | 2022-02-11 | B class pipes | Co ordinate with Leela krishna granite supplier fro delivery
164557 | 2022-02-16 | SS Bain marie and bottle cooler ctc., | Material under manufacturing
164570 | 2022-02-17 | Checkred plates | Deliverd
164580 | 2022-02-18 | MS Sandwich panel | Co ordinate with Leela krishna granite supplier fro delivery
164585 | 2022-02-18 | Wash basin | Co ordinate with Leela krishna granite supplier fro delivery
164593 | 2022-02-19 | SS Railing | Work under progress
164596 | 2022-02-19 | Steel sign boards | Co ordinate with Leela krishna granite supplier fro delivery
164605 | 2022-02-22 | 40 mm square pipe | Deliverd
164611 | 2022-02-23 | MS Rectanguler plates | Deliverd
164614 | 2022-02-23 | Dummy flanges dummy bend | Deliverd
164639 | 2022-02-26 | SS Railing | Work under progress
164650 | 2022-03-03 | Indigo ACE waterline | Its solar panel, quotes to be receive
164677 | 2022-03-07 | Coper flexible cable 2 core aluminium lugs | Deliverd
164681 | 2022-03-07 | Die grinder | Co ordinate with Leela krishna granite supplier fro delivery