## Sheet1
Prepared by: |  | P.Prabhakar
Report Date |  | 2022-03-12
Site |  | MPL
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
178270 | 24.2.2021 | EPDM flooring | Rates under negotiation
178301 | 06.01.2022 | Jerry cans | Online purchase
178310 | 11.01.2022 | Playground area equipment | Estimate to be prepare
178314 | 11.01.2022 | SS Railing | PO to be issued
178316 | 11.01.2022 | Sensor type urinal,Urinal waster coupling | PO to be issued
178327 | 19.01.2022 | Router TP link | On line purchase
178328 | 20.01.2022 | 3 way rocker | PO to be issued
178342 | 24.01.2022 | Control panel for pump | PO to be issued
178369 | 05.02.2022 | Executive bag | Online purchase
178397 | 21.02.2022 | Sliding windows | PO to be issued
178409 | 05.03.2022 | Cartridge | PO to be issued
List of requisitions where PO/WO is prepared and items have not been received at site beyond the lead time:
177487 | 18.03.2021 | MCBs,modular plate ,socket | Bulk order, Part material delivered, remaining material available at supplier will be delivered next week.
177488 | 18.03.2021 | MCBs,modular plate ,socket | Bulk order, Part material delivered, remaining material available at supplier will be delivered next week.
177498 | 19.03.2021 | Stainless steel sink | Bulk order, Part material delivered, remaining material available at supplier will be delivered next week.
177901 | 07.08.2021 | Urban wood natural | Part material received. Remaining material no stock at Supplier
178112 | 20.10.2021 | Garbage Bin | Part material received. Remaining material no stock at Supplier
178122 | 26.10.2021 | UPVC Windows | Work under progress
178125 | 29.10.2021 | Wall mixtures | Bulk order, Part material delivered, remaining material available at supplier will be delivered next week.
178126 | 29.10.2021 | Wall mixtures | Bulk order, Part material delivered, remaining material available at supplier will be delivered next week.
178127 | 29.10.2021 | Wall hung WC | Bulk order, Part material delivered, remaining material available at supplier will be delivered next week.
178128 | 29.10.2021 | Wall hung WC | Bulk order, Supplier has the material, delivery by next week
178152 | 08.11.2021 | Urban wood natural & Crema marfil | Part material received remaining material no stock at supplier
178191 | 23.11.2021 | Glass partition | Part material delivered, Work under progress
178208 | 30.11.2021 | UPVC Windows | Work under progress
178268 | 24.12.2021 | DB Board single phase | Part material received remaining material delivery in next week
178302 | 07.01.2022 | UPVC windows | Work under progress
178304 | 07.01.2022 | UPVC windows | Work under progress
178311 | 11.01.2022 | UPVC sliding windows | Work under progress
178312 | 11.01.2022 | Glass partition | Work under progress
178317 | 12.01.2022 | UPVC sliding windows | Work under progress
178361 | 02.02.2022 | UPVC windows | Work under progress
178366 | 02.02.2022 | Regal biege | Supplier arranging material
178377 | 08.02.2022 | DAP | Deliverd
178381 | 10.02.2022 | Inwall tank | Delivery in next week
178386 | 12.02.2022 | L angle brackets | Delivery in next week
178396 | 21.02.2022 | Kitchenunit | Delivery in next week .
178399 | 23.02.22 | Pvc flase ceiling sheets | Deliverd
178407 | 03.03.2022 | Fruit packing covers | Deliverd
178408 | 04.03.2022 | Flush plate | Pick up from SSLLP
178413 | 05.03.2022 | Pvc pipes | Deliverd
178417 | 07.03.2022 | Roff chemical | Deliverd
178418 | 07.03.2022 | Tile grout | Deliverd