## Vista
Prepared by: | vanajakshi
Report Date | 21.03.2022
Site | Serene Farms
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
150604 | 20.11.2021 | Curtain | Po to be issue
150605 | 20.11.2021 | Curtain rods | Po to be issue
150603 | 20.11.2021 | Acrylic board | Po to be issue
List of requisitions Where PO/WO is prepared and items have not received at site
150596 | 18.10.2021 | Sub merisble pump | Follow up with supplier
150619 | 22.02.2022 | Sanitsry | Delivered
150620 | 24.02.2022 | Plumbing | Delivered
150622 | 07.03.2022 | Electrical | Delivered
150623 | 07.03.2022 | Green hose pipe | Delivered