## VOC LLP
Prepared by: | Mounika
Report Date | 21.03.22
Site | Nxetopolis
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
186217 | 02.02.22 | Memory card | Online purchase
186211 | 29.01.22 | GI Tower | Requisition sent to MD Approval
186208 | 28.01.22 | WI FI Router | Online purchase
186230 | 19.02.22 | Land line phone | Online purchase
186233 | 19.02.22 | Tea Flask | Local Purchase
186233 | 19.02.22 | Metna | Local Purchase
186244 | 03.03.22 | Cameras with solar Panels | Quotes to receive
List of requisitions Where PO/WO is prepared and items have not received at site
186247 | 08.03.22 | Govess, Shoes | Ready With supplier
186240 | 28.02.22 | FRP Thadkas | Ready With supplier
186250 | 15.03.22 | Steel | Delivered
186248 | 08.03.22 | Canvas pipe with Couplers | Ready With supplier