## KNM
Prepared by: | Kavitha
Report Date | 25-03-2022
Site | AGH
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
165580 | 2022-02-11 | Pressure Mechine | Enquiry in market
List of requisitions Where PO/WO is prepared and items have not received at site
Follow up with suppleir
165582 | 28-02-2022 | MS Railing | We are arranging for material
165584 | 2022-01-03 | CP Items | We are arranging for material