## KNM
Prepared by: | Kavitha
Report Date | 18-03-2022
Site | MRGV
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
95063 | 2022-11-02 | Callisto AC CTY00034 tiles | Req.send to MD's Approval
95083 | 16-03-2022 | GYM room material | Po to issue
95084 | 16-03-2022 | Yoga mat, digital weighing machine | Po to issue
95085 | 16-03-2022 | Recreation room material | Po to issue
95086 | 16-03-2022 | Cafeterial material | Po to issue
95089 | 16-03-2022 | Gardening material | Po to issue
95090 | 16-03-2022 | Split AC casette AC | Po to issue
95091 | 16-03-2022 | Cretch toilet material | Po to issue
95093 | 16-03-2022 | Mirror with frame | Po to issue
95094 | 16-03-2022 | Low storage | Po to issue
List of requisitions Where PO/WO is prepared and items have not received at site
Follow up with suppleir
95068 | 25-02-2022 | Wifi router | Contact Sunil sir
95075 | 2022-04-03 | stationery | Pick up from SSLLP
95078 | 2022-07-03 | Flat files | Follow up with promotions
95080 | 2022-07-03 | CPVC Material | Pick up from SSLLP
95081 | 2022-03-11 | Measurement tapes | Pick up from SSLLP
95082 | 15-03-2022 | Cretch room material | Contact supplier
95088 | 16-03-2022 | RO Plant | Contact supplier
95092 | 16-03-2022 | Chair without caster | Contact supplier
95095 | 16-03-2022 | Floor mat | Contact supplier