## VOC LLP
Prepared by: | Mounika
Report Date | 26.03.22
Site | Nxetopolis
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
186217 | 02.02.22 | Memory card | Online purchase
186211 | 29.01.22 | GI Tower | Requisition sent to MD Approval
186208 | 28.01.22 | WI FI Router | Online purchase
186230 | 19.02.22 | Land line phone | Online purchase
186233 | 19.02.22 | Tea Flask | Local Purchase
186233 | 19.02.22 | Metna | Delivered
186244 | 03.03.22 | Cameras with solar Panels | Quotes to receive
186252 | 26.03.22 | MS Buckets | Po to be issue
List of requisitions Where PO/WO is prepared and items have not received at site
186247 | 08.03.22 | Govess, Shoes | Ready With supplier
186248 | 08.03.22 | Canvas pipe with Couplers | Ready With supplier
186240 | 28.02.22 | MS Thadkas | Ready With supplier