## Sheet1
Prepared by: |  | P.Prabhakar
Report Date |  | 2022-03-20
Site |  | MPL
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
178270 | 24.2.2021 | EPDM flooring | Quotes to be received
178301 | 06.01.2022 | Jerry cans | Online purchase
178310 | 11.01.2022 | Playground area equipment | PO in estimate
178314 | 11.01.2022 | SS Railing | PO to be issued
178316 | 11.01.2022 | Sensor type urinal,Urinal waster coupling | PO to be issued
178327 | 19.01.2022 | Router TP link | On line purchase
178328 | 20.01.2022 | 3 way rocker | PO to be issued
178342 | 24.01.2022 | Control panel for pump | PO to be issued
178369 | 05.02.2022 | Executive bag | Online purchase
178397 | 21.02.2022 | Sliding windows | PO to be issued
178409 | 05.03.2022 | Cartridge | PO to be issued
178437 | 17.03.2022 | Wall mounted | PO to be issued
List of requisitions where PO/WO is prepared and items have not been received at site beyond the lead time:
177487 | 18.03.2021 | MCBs,modular plate ,socket | Bulk order, Part material delivered, remaining material available at supplier will be delivered next week.
177488 | 18.03.2021 | MCBs,modular plate ,socket | Bulk order, Part material delivered, remaining material available at supplier will be delivered next week.
177498 | 19.03.2021 | Stainless steel sink | Bulk order, Part material delivered, remaining material available at supplier will be delivered next week.
178122 | 26.10.2021 | UPVC Windows | Work under progress
178125 | 29.10.2021 | Wall mixtures | Bulk order, Part material delivered, remaining material available at supplier will be delivered next week.
178126 | 29.10.2021 | Wall mixtures | Bulk order, Part material delivered, remaining material available at supplier will be delivered next week.
178127 | 29.10.2021 | Wall hung WC | Bulk order, Part material delivered, remaining material available at supplier will be delivered next week.
178128 | 29.10.2021 | Wall hung WC | Bulk order, Supplier has the material, delivery by next week
178191 | 23.11.2021 | Glass partition | Part material delivered, Work under progress
178208 | 30.11.2021 | UPVC Windows | Work under progress
178268 | 24.12.2021 | DB Board single phase | Part material received remaining material to de received . no stock at ssllp .
178302 | 07.01.2022 | UPVC windows | Work under progress
178304 | 07.01.2022 | UPVC windows | Work under progress
178311 | 11.01.2022 | UPVC sliding windows | Work under progress
178312 | 11.01.2022 | Glass partition | Work under progress
178317 | 12.01.2022 | UPVC sliding windows | Work under progress
178361 | 02.02.2022 | UPVC windows | Work under progress
178381 | 10.02.2022 | Inwall tank | Delivery in next week
178396 | 21.02.2022 | Kitchenunit | Delivery in next week .
178407 | 03.03.2022 | Fruit packing covers | Material will be delivered next week .
178408 | 04.03.2022 | Flush plate | Material will be delivered next week .
178423 | 11.03.2022 | Paints | Material will be delivered today .
178426 | 12.03.2022 | Pavers | Material will be delivered today .
178428 | 14.03.2022 | Plywood | Material will be delivered next week .
178429 | 14.03.2022 | Powder | Material will be delivered today .
178430 | 15.03.2022 | CP Jali | Material will be delivered today .`
178432 | 15.03.2022 | Flush plates | Material will be delivered today .`