## VOC LLP
Prepared by: | Mounika
Report Date | 04.04.22
Site | Nxetopolis
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
186217 | 02.02.22 | Memory card | Online purchase
186208 | 28.01.22 | WI FI Router | Online purchase
186230 | 19.02.22 | Land line phone | Online purchase
186234 | 19.02.22 | Tea Flask | Local Purchase
186233 | 19.02.22 | Metna | Delivered
186260 | 03.03.22 | Biometric battery | Online purchase
186253 | 21.03.22 | Gova ballies | Local Purchase
List of requisitions Where PO/WO is prepared and items have not received at site
186258 | 25.03.22 | Electical Vibrator | Ready With supplier
186240 | 28.02.22 | MS Thadkas | Ready With supplier