## Vista
Prepared by: | vanajakshi
Report Date | 07.04.2022
Site | Serene Farms
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
150628 | 31.03.2022 | Green hose pipe | PO Number:87148
150626 | 28.03.2022 | Tube lights | PO number:86903
List of requisitions Where PO/WO is prepared and items have not received at site
150626 | 28.03.2022 | electrical | Follow up with supplier
150514 | 31.03.2022 | Tan brown granite | Next week deliver
150628 | 31.03.2022 | PVC | Next week deliver