## Sheet1
Prepared by: |  | P.Prabhakar
Report Date |  | 2022-03-26
Site |  | MPL
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
178270 | 24.2.2021 | EPDM flooring | PO 87055, 87056
178301 | 06.01.2022 | Jerry cans | No stock cancelled
178310 | 11.01.2022 | Playground area equipment | POM85190
178314 | 11.01.2022 | SS Railing | PO to be issued
178316 | 11.01.2022 | Sensor type urinal,Urinal waster coupling | Missing requisition, po to be issue
178327 | 19.01.2022 | Router TP link | Cancelled
178328 | 20.01.2022 | 3 way rocker | Po issued with another req close this req
178342 | 24.01.2022 | Control panel for pump | Cancelled by MD
178369 | 05.02.2022 | Executive bag | PO 87232
178437 | 2022-03-17 | Pedestal fan | PO 86895
178447 | 2022-03-23 | MI Camera | PO 86967
178448 | 2022-03-23 | Landline phone | PO 87226
List of requisitions where PO/WO is prepared and items have not been received at site beyond the lead time:
177487 | 18.03.2021 | MCBs,modular plate ,socket | Bulk order, Part material delivered, remaining material available at supplier will be delivered next week.
177488 | 18.03.2021 | MCBs,modular plate ,socket | Bulk order, Part material delivered, remaining material available at supplier will be delivered next week.
177498 | 19.03.2021 | Stainless steel sink | Bulk order, Part material delivered, remaining material available at supplier will be delivered next week.
178122 | 26.10.2021 | UPVC Windows | Work under progress
178125 | 29.10.2021 | Wall mixtures | Bulk order, Part material delivered, remaining material available at supplier will be delivered next week.
178126 | 29.10.2021 | Wall mixtures | Bulk order, Part material delivered, remaining material available at supplier will be delivered next week.
178127 | 29.10.2021 | Wall hung WC | Bulk order, Part material delivered, remaining material available at supplier will be delivered next week.
178128 | 29.10.2021 | Wall hung WC | Bulk order, Supplier has the material, delivery by next week
178191 | 23.11.2021 | Glass partition | Part material delivered, Work under progress
178208 | 30.11.2021 | UPVC Windows | Work under progress
178268 | 24.12.2021 | DB Board single phase | Part material received remaining material to de received . no stock at ssllp .
178302 | 07.01.2022 | UPVC windows | Work under progress
178304 | 07.01.2022 | UPVC windows | Work under progress
178311 | 11.01.2022 | UPVC sliding windows | Work under progress
178312 | 11.01.2022 | Glass partition | Work under progress
178317 | 12.01.2022 | UPVC sliding windows | Work under progress
178361 | 02.02.2022 | UPVC windows | Work under progress
178381 | 10.02.2022 | Inwall tank | Deliverd
178396 | 21.02.2022 | Kitchenunit | Delivery in next week .
178397 | 2022-02-21 | Sliding windows | Work under progress
178428 | 14.03.2022 | Plywood | Pick up from Sri sai rohit marketing
178430 | 15.03.2022 | CP Jali | Co ordinate with supplier for delivery
178432 | 15.03.2022 | Flush plates | Deliverd
178422 | 2022-03-11 | Lawn mover | Co ordinate with supplier for delivery
178440 | 2022-03-21 | Grills | Deliverd
178442 | 2022-03-11 | Tiles | Pick up from SSLLP-GMR
178444 | 2022-03-22 | Tan brown granite | Deliverd
178443 | 23-23-22 | Tan brown granite | Deliverd
178446 | 2022-03-23 | PVC Sheets | Deliverd
178445 | 2022-03-23 | False ceiling | Work under process