## Vista
Prepared by: | vanajakshi
Report Date | 11.03.2022
Site | Serene farms
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
Nil |  | Nil | Nil
List of requisitions Where PO/WO is prepared and items have not received at site
150596 | 18.10.2021 | Submersible pump | Sent to MD'S approval
150619 | 22.02.2022 | Sanitary | Next week deliver
150620 | 24.02.2022 | Plumbing | Next week deliver