## Sheet1
Prepared by: |  | P.Prabhakar
Report Date |  | 2022-04-04
Site |  | MPL
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
178270 | 24.2.2021 | EPDM flooring | PO 87055, 87056
178301 | 06.01.2022 | Jerry cans | No stock cancelled
178310 | 11.01.2022 | Playground area equipment | PO 85190
178314 | 11.01.2022 | SS Railing | PO to be issued
178316 | 11.01.2022 | Sensor type urinal,Urinal waster coupling | Missing requisition, po to be issue
178327 | 19.01.2022 | Router TP link | Cancelled
178328 | 20.01.2022 | 3 way rocker | Po issued with another req close this req
178448 | 2022-03-23 | Landline phone | PO 87226
178453 | 2022-03-26 | Gas cylender | PO 87203
178457 | 2022-03-26 | First aid room material | PO to be issued
178458 | 2022-03-26 | Gym material | PO 87218
178466 | 2022-03-29 | Gym material | Po issued with another req close this req
178469 | 2022-03-29 | Cafeteria material | PO 86948
178470 | 2022-03-29 | Low storage | PO to be issued
178471 | 2022-03-29 | Party speaker | PO 86887, Part speaker po to be issue
178472 | 2022-03-29 | Paper dispenser | PO 86874
List of requisitions where PO/WO is prepared and items have not been received at site beyond the lead time:
177487 | 18.03.2021 | MCBs,modular plate ,socket | Bulk order, Part material delivered, remaining material available at supplier will be delivered next week.
177488 | 18.03.2021 | MCBs,modular plate ,socket | Bulk order, Part material delivered, remaining material available at supplier will be delivered next week.
177498 | 19.03.2021 | Stainless steel sink | Bulk order, Part material delivered, remaining material available at supplier will be delivered next week.
178122 | 26.10.2021 | UPVC Windows | Work under progress
178125 | 29.10.2021 | Wall mixtures | Bulk order, Part material delivered, remaining material available at supplier will be delivered next week.
178126 | 29.10.2021 | Wall mixtures | Bulk order, Part material delivered, remaining material available at supplier will be delivered next week.
178127 | 29.10.2021 | Wall hung WC | Bulk order, Part material delivered, remaining material available at supplier will be delivered next week.
178128 | 29.10.2021 | Wall hung WC | Bulk order, Supplier has the material, delivery by next week
178191 | 23.11.2021 | Glass partition | Part material delivered, Work under progress
178208 | 30.11.2021 | UPVC Windows | Work under progress
178268 | 24.12.2021 | DB Board single phase | Part material received remaining material to de received . no stock at ssllp .
178302 | 07.01.2022 | UPVC windows | Work under progress
178304 | 07.01.2022 | UPVC windows | Work under progress
178311 | 11.01.2022 | UPVC sliding windows | Work under progress
178312 | 11.01.2022 | Glass partition | Work under progress
178317 | 12.01.2022 | UPVC sliding windows | Work under progress
178361 | 02.02.2022 | UPVC windows | Work under progress
178381 | 10.02.2022 | Inwall tank | Deliverd
178396 | 21.02.2022 | Kitchenunit | Delivery in next week .
178397 | 2022-02-21 | Sliding windows | Work under progress
178428 | 14.03.2022 | Plywood | Pick up from Sri sai rohit marketing
178430 | 15.03.2022 | CP Jali | Co ordinate with supplier for delivery
178432 | 15.03.2022 | Flush plates | Deliverd
178422 | 2022-03-11 | Lawn mover | Co ordinate with supplier for delivery
178440 | 2022-03-21 | Grills | Deliverd
178442 | 2022-03-11 | Tiles | Pick up from SSLLP-GMR
178445 | 2022-03-23 | False ceiling | Work under process
178449 | 2022-03-25 | Roff chemical | Deliverd
178452 | 2022-03-25 | Sliding windows | Work under process
178455 | 2022-03-26 | Creche equipments | Co ordinate with supplier for delivery
178456 | 2022-03-26 | Creche equipments | Co ordinate with supplier for delivery
178464 | 2022-03-29 | Benches | Co ordinate with supplier for delivery
178465 | 2022-03-29 | Notice board | Pick up from SSLLP.
178467 | 2022-03-29 | Recreation material | Co ordinate with supplier for delivery
178468 | 2022-03-29 | Play ground equipments | Co ordinate with supplier for delivery
178473 | 2022-03-29 | Mirror with frame | Co ordinate with supplier for delivery