## GVRC
Prepared by: |  | P.Prabhakar
Report Date |  | 2022-04-02
Site |  | GVRC
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
164173 | 2021-11-22 | FRP Manholes | Cancell this requisition and send a new requisition
164436 | 2022-01-18 | 1 hp pump, with suitable pipe, diesel hand pump | Cancelled by MD
164632 | 2022-02-24 | Horizantal centrifugal motor guard | Cancelled by MD
164664 | 2022-03-05 | Digital water meter, normal meter | Cancelled by MD
164666 | 2022-03-05 | STP Water proofing | Requisition not found in email send it again
164668 | 2022-03-05 | Epoxy coat water proofing | Requisition not found in email send it again
164669 | 2022-03-05 | Water proofing for sumps | Requisition not found in email send it again
164695 | 2022-03-09 | White colour reflector | PO 86949
164725 | 2022-03-15 | Box strapping machine | Locall purchased, deliverd to site
164729 | 2022-03-15 | Machine wire brush | Locall purchased, deliverd to site
164732 | 2022-03-16 | CIF Power and bruch | Local purchased
164734 | 2022-03-16 | Scrubbing wheels | Local purchased
164736 | 2022-03-16 | AC Electric voltage powerdector | PO 87132
164740 | 2022-03-18 | FRP Square covers | Cancelled by site
164755 | 2022-03-22 | Flush pipe with rubber washer | PO 87040
164756 | 2022-03-22 | Pressure switch | PO 86988
164757 | 2022-03-22 | Red paint | PO 86928
164777 | 2022-03-28 | Wires | PO 86816
164780 | 2022-03-28 | 24V, 20A Battery charger | PO to be issue
164788 | 2022-03-30 | Steel sign board
164791 | 2022-03-31 | 4 core aluminium armor cable | PO to be issue
List of requisitions Where PO/WO is prepared and items have not received at site
163704 | 2021-08-07 | ACP cladding | Work under progress
164011 | 2021-12-08 | Busduct material | Work under progress
164260 | 2021-12-08 | Goods lift | Work under progress
164366 | 2021-12-30 | GI Piping wrapping material | Follow up with supplier for delivery
164457 | 2022-01-22 | SS Railing | Co ordinate with Leela krishna granite supplier fro delivery
164593 | 2022-02-19 | SS Railing | Work under progress
164644 | 2022-02-22 | Greenlam sturdo classique versitlile | Co ordinate with Leela krishna granite supplier fro delivery
164677 | 2022-03-07 | Copper flexible cable 2 core aluminium lugs | Deliverd
164701 | 2022-03-09 | ISMB Channel | Deliverd
164706 | 2022-03-10 | PVC Pipe | Deliverd
164742 | 2022-03-19 | 2 core copper flexible cable | Deliverd
164743 | 2022-03-19 | Plain dummy | Co ordinate with Leela krishna granite supplier fro delivery
164744 | 2022-03-19 | SS Railing | Work under progress
164755 | 2022-03-22 | Flush pipe with rubber washer | Deliverd
164759 | 2022-03-23 | Hakshw blade | Deliverd
164771 | 2022-03-26 | Cutting wheels | Deliverd
164783 | 2022-03-28 | Wlding rods | Co ordinate with Leela krishna granite supplier fro delivery