## KNM
Prepared by: | Kavitha
Report Date | 2022-07-04
Site | MRGV
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
95063 | 2022-11-02 | Callisto AC CTY00034 tiles | Req.send to MD's Approval
95083 | 16-03-2022 | GYM room material | PO issued-Po no-86566, 87219
95084 | 16-03-2022 | Yoga mat, digital weighing machine | Po to issued
95085 | 16-03-2022 | Recreation room material | PO Issued- PO no-87157
95086 | 16-03-2022 | Cafeterial material | PO Issued- PO no-87059
95089 | 16-03-2022 | Gardening material | PO Issued- PO no-86715
95090 | 16-03-2022 | Split AC casette AC | Quotes to be receive
95091 | 16-03-2022 | Cretch toilet material | PO Issued- PO no-86565, 86627
95093 | 16-03-2022 | Mirror with frame | PO Issued- PO no-86920
95094 | 16-03-2022 | Low storage | Po to issued
List of requisitions Where PO/WO is prepared and items have not received at site
Follow up with suppleir
95081 | 2022-03-11 | Measurement tapes | Pick up from SSLLP
95082 | 15-03-2022 | Cretch room material | Contact supplier
95088 | 16-03-2022 | RO Plant | Contact supplier
95091 | 16-03-2022 | SS Dust bin | Contact supplier
95095 | 16-03-2022 | Floor mat | Contact supplier