## KNM
Prepared by: | Kavitha
Report Date | 2022-07-04
Site | AGH
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
165580 | 2022-02-11 | Pressure machine | Cancelled
165598 | 19-03-2022 | Kitchen items | PO issued-PO no-87213
165600 | 19-03-2022 | First aid room items | PO issued
165601 | 19-03-2022 | Gym items | PO issued-PO no-86922
165608 | 19-03-2022 | Swimming pool items | PO issued-PO no-87251, 87252
165609 | 19-03-2022 | Sociaty office items | PO issued-PO no-87063
165617 | 31-03-2022 | Consumable material | PO issued
165618 | 31-03-2022 | Stationery Office used | PO issued-PO no-87269
List of requisitions Where PO/WO is prepared and items have not received at site
Follow up with suppleir
165577 | 18-02-2022 | Wall mounted urinal | Send to SSLLP
165584 | 2022-03-01 | CP Items for clubhouse | Next week delivery
165597 | 19-03-2022 | Banquet hall itema | 15% delivered, remaining to be delivered by next week
165599 | 19-03-2022 | Crech items | Next week delivery
165602 | 19-03-2022 | Recreation items | Next week delivery
165603 | 19-03-2022 | Cfeteria | Next week delivery
165604 | 19-03-2022 | Playground Eqipment | Next week delivery
165605 | 19-03-2022 | Housekeeping itema | Next week delivery
165606 | 19-03-2022 | Light items | 20% delivered, remaining to be delivered by next week
165607 | 19-03-2022 | Toilet items | 40% delivered, remaining to be delivered by next week
165612 | 24-03-2022 | Paint material | Next week delivery
165613 | 25-03-2022 | MS Gate with material | Next week delivery
16514 | 29-03-2022 | Sadarali granite top | Next week delivery
165615 | 29-03-2022 | 4x2 floor tiles | Next week delivery
165616 | 31-03-2022 | 4x2 floor tiles | Next week delivery