## VOC LLP
Prepared by: | Mounika
Report Date | 11.04.22
Site | Nxetopolis
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
186217 | 02.02.22 | Memory card | Cancelled
186208 | 28.01.22 | WI FI Router | Cancelled
186230 | 19.02.22 | Land line phone | Online purchase
186234 | 19.02.22 | Tea Flask | Cancelled
186263 | 04.04.22 | Deisel cans | Local Purchase
186260 | 03.03.22 | Biometric battery | Online purchase
186253 | 21.03.22 | Gova ballies | Local Purchase
186231 | 29.03.22 | Octagonal poles | Po to be issue
186211 | 29.01.22 | GI Tower | Cancelled
186254 | 21.03.22 | Plastic Drums | Po to be issue
List of requisitions Where PO/WO is prepared and items have not received at site
186266 | 08.04.22 | Measuring Tapes | Delivered
186265 | 08.04.22 | Vim bars | Delivered
186264 | 08.04.22 | Safety Ribbon | Delivered
186244 | 03.03.22 | Cameras with Solar Pannel | This week Delivary
186240 | 28.02.22 | MS Tadaka | Collect at SSLLP