## Vista
Prepared by: | vanajakshi
Report Date | 19.04.2022
Site | Serene Farms
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
150629 | 13.04.2022 | Submersible pump | Po to be issue
List of requisitions Where PO/WO is prepared and items have not received at site
150626 | 28.03.2022 | Electrical | Deliver by this week
150628 | 31.03.2022 | Plumbing | Deliver by this week