## VOC LLP
Prepared by: | Mounika
Report Date | 16.04.22
Site | Nxetopolis
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
186267 | 11.01.22 | Plates | Local Purchase
186263 | 04.04.22 | Deisel cans | Local Purchase
186260 | 03.03.22 | Biometric battery | Online purchase
186231 | 29.03.22 | Octagonal poles | Po to be issue
186254 | 21.03.22 | Plastic Drums | Local Purchase
List of requisitions Where PO/WO is prepared and items have not received at site
186244 | 03.03.22 | Cameras with Solar Pannel | This week Delivary