## KNM
Prepared by: | Kavitha
Report Date | 22-04-2022
Site | MRGV
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
95063 | 2022-02-11 | Callisto AC CTY00034 Tiles | requisition send to md approval
95083 | 16-03-2022 | GYM room material | PO issued-Po no-86566, 87219
95084 | 16-03-2022 | Yoga mat, digital weighing machine | Po to issued
95088 | 16-03-2022 | Bosch pressure cleaner | PO issued-Po no-86493, 87197
95086 | 16-03-2022 | Cafeterial material | PO Issued- PO no-87059
95089 | 16-03-2022 | Gardening material | PO Issued- PO no-86715
95090 | 16-03-2022 | Split AC casette AC | Quotes to be receive
95091 | 16-03-2022 | Cretch toilet material | PO Issued- PO no-86565, 86627
95094 | 16-03-2022 | Low storage | Po to issued
List of requisitions Where PO/WO is prepared and items have not received at site
Follow up with suppleir
95082 | 16-03-2022 | Cretch toilet material | Contact supplier
95085 | 16-03-2022 | Recreation room material | Contact supplier
95087 | 16-03-2022 | RO Plant | Contact supplier
95088 | 16-03-2022 | Bosch pressure cleaner | Contact supplier
95093 | 16-03-2022 | Mirror with frame | Pick up from supplier
95095 | 16-03-2022 | Floor mat | Contact supplier
95097 | 23-03-2022 | Switches | Pick up from SSLLP
95100 | 24-03-2022 | Recron | Pick up from SSLLP
95103 | 24-03-2022 | Breath Analyser | Online purchase
95109 | 2022-04-04 | CPVC Material | Pick up from SSLLP