## KNM
Prepared by: | Kavitha
Report Date | 22-04-2022
Site | AGH
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
165600 | 19-03-2022 | First Aid room items | Po to be issue
165684 | 2022-03-08 | Counter top pillar tap | Wrong requisition no. mentioned
List of requisitions Where PO/WO is prepared and items have not received at site
Follow up with suppleir
165572 | 31-01-2022 | Panel doors | 15% delivered We are arranging remaining material
165597 | 19-03-22 | Bnquet hall items | 70% delivered We are arranging remaining material
165599 | 19-03-2022 | Cretch items | 10% delivered We are arranging remaining material
165601 | 19-03-2022 | GYM items | Next week delivery
165602 | 19-03-2022 | Recreation items | Next week delivery
165603 | 19-03-2022 | Cafeteria | 50% delivered We are arranging remaining material
165604 | 19-03-2022 | Plyground Equipment | Next week delivery
165606 | 19-03-2022 | Light items | 80% delivered We are arranging remaining material
165607 | 19-03-2022 | Toilet items | 40% delivered We are arranging remaining material
165609 | 19-03-2022 | Sociaty Office items | Next week delivery
165613 | 25-03-2022 | MS Gates with material | Next week delivery
165614 | 29-03-2022 | Sadarali garanite top | Next week delivery
165615 | 29-03-2022 | 4x2 floor tiles | Next week delivery
165616 | 31-03-2022 | 4x2 floor tiles | Next week delivery
165617 | 2022-11-04 | Consumable material | Next week delivery
165619 | 2022-06-04 | CPVC items | Next week delivery
165620 | 2022-06-04 | PVC items | Next week delivery
165621 | 2022-06-04 | Eco drain items | Next week delivery
165624 | 2022-09-04 | Urinal | Next week delivery