## Vista
Prepared by: | vanajakshi
Report Date | 25.04.2022
Site | Serene Farms
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
150635 | 21.04.2022 | Curtain rods | Po to be issue
150634 | 21.04.2022 | Curtains | Po to be issue
150629 | 11.04.2022 | Submersible pump | Resending the requisition to MD
List of requisitions Where PO/WO is prepared and items have not received at site
150626 | 28.03.2022 | Electrical | Deliver by this week
150628 | 31.03.2022 | PVC | Follow up with supplier
150631 | 18.04.2022 | Electrical | Deliver by this week