## VOC LLP
Prepared by: | Mounika
Report Date | 25.04.22
Site | Nxetopolis
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
186267 | 11.01.22 | Plates | Local Purchase
186263 | 04.04.22 | Deisel cans | Local Purchase
186260 | 03.03.22 | Biometric battery | Online purchase
186231 | 29.03.22 | Octagonal poles | Po to be issue
186254 | 21.03.22 | Plastic Drums | Local Purchase
186293 | 20.04.22 | Wifi router | Online purchase
List of requisitions Where PO/WO is prepared and items have not received at site
186296 | 20.04.22 | LED Lights | Delivered
186295 | 20.04.22 | Service wire | Delivered
186289 | 19.04.22 | L-angle | Pick from Supplier
186288 | 19.04.22 | HDPE rope | Pick from Supplier
186282 | 18.04.22 | Flat patti | Pick from Supplier
186281 | 18.04.22 | L-angle | Pick from Supplier
186280 | 18.04.22 | MS Round pipe | Pick from Supplier
186279 | 18.04.22 | Safety nets | Pick from SSLLP
186277 | 16.04.22 | Armour cable | Pick from Supplier
186273 | 19.04.22 | Green Hose Pipe | Delivered
186272 | 16.04.22 | Blue sheets | Delivered
186271 | 16.04.22 | Covering Blocks | Delivered
186269 | 15.04.22 | Hand Gloves | Pick from Supplier