## KNM
Prepared by: | Kavitha
Report Date | 28-04-2022
Site | AGH
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
165625 | 16-04-2022 | Off white plated blinds | Po to be issue
165600 | 19-03-2022 | First aid room items | Po to be issue
165684 | 2022-03-08 | Counter top pillar tap | Wrong req. no. mentioned
List of requisitions Where PO/WO is prepared and items have not received at site
Follow up with suppleir
165572 | 31-01-22 | Panel doors | 15% delivered, remaining to be delivered by next week
165597 | 19-03-2022 | Banquet hall itema | 15% delivered, remaining to be delivered by next week
165599 | 19-03-2022 | Crech items | Next week delivery
165601 | 19-03-2022 | Gym items | Next week delivery
165602 | 19-03-2022 | Recreation items | Next week delivery
165603 | 19-03-2022 | Cfeteria | Next week delivery
165604 | 19-03-2022 | Playground Eqipment | Next week delivery
165606 | 19-03-2022 | Light items | 20% delivered, remaining to be delivered by next week
165607 | 19-03-2022 | Toilet items | 40% delivered, remaining to be delivered by next week
165609 | 19-03-2022 | Sociaty office items | Next week delivery
165613 | 25-03-2022 | MS Gate with material | Next week delivery
16514 | 29-03-2022 | Sadarali granite top | Next week delivery
165615 | 29-03-2022 | 4x2 floor tiles | Next week delivery
165616 | 31-03-2022 | 4x2 floor tiles | Next week delivery
165621 | 2022-04-10 | 315 raiser | Next week delivery
165622 | 2022-04-16 | electrical switches | Next week delivery
165626 | 18-04-2022 | carpet grass | Next week delivery