## Vista
Prepared by: | vanajakshi
Report Date | 19.04.2022
Site | Serene Farms
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
150635 | 21.04.2022 | Curtain rods | Online purchase
150634 | 21.04.2022 | Curtains | PO to be issue
150629 | 11.04.2022 | Submersible pump | PO to be issue
List of requisitions Where PO/WO is prepared and items have not received at site
150626 | 28.04.2022 | electrical | Deliver by this week
150628 | 31.03.2022 | PVC | PO closed
150631 | 18.04.2022 | electrical | Deliver by this week
150637 | 28.04.2022 | Papers | Deliver by this week
150636 | 28.04.2022 | Plumbing | Deliver by this week