## Sheet1
Prepared by: |  | P.Prabhakar
Report Date |  | 2022-04-30
Site |  | MPL
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
178270 | 24.2.2021 | EPDM flooring | PO 87055, 87056
178301 | 06.01.2022 | Jerry cans | No stock cancelled
178310 | 11.01.2022 | Playground area equipment | PO 85190
178314 | 11.01.2022 | SS Railing | Cancell this requisition and raise the new one with lateset date
178316 | 11.01.2022 | Sensor type urinal,Urinal waster coupling
178327 | 19.01.2022 | Router TP link | Cancelled
178328 | 20.01.2022 | 3 way rocker | Po issued with another req close this req
178469 | 2022-03-29 | Cafeteria material | PO 86948
178470 | 2022-03-29 | Sofa set | PO 87543
178471 | 2022-03-29 | Part speaker | Po to be issue
178472 | 2022-03-29 | Paper dispenser | PO86874
178515 | 2022-04-18 | HOB and Chimney | Quotes to be receive
178524 | 2022-04-26 | LED Lights | PO 87804
178525 | 2022-04-26 | Ceiling fans | PO 87943
178526 | 2022-04-26 | Plywood | PO 87841
List of requisitions where PO/WO is prepared and items have not been received at site beyond the lead time:
177487 | 18.03.2021 | MCBs,modular plate ,socket | Bulk order, Part material delivered, remaining material available at supplier will be delivered next week.
177488 | 18.03.2021 | MCBs,modular plate ,socket | Bulk order, Part material delivered, remaining material available at supplier will be delivered next week.
177498 | 19.03.2021 | Stainless steel sink | Bulk order, Part material delivered, remaining material available at supplier will be delivered next week.
178122 | 26.10.2021 | UPVC Windows | Work under progress
178125 | 29.10.2021 | Wall mixtures | Bulk order, Part material delivered, remaining material available at supplier will be delivered next week.
178126 | 29.10.2021 | Wall mixtures | Bulk order, Part material delivered, remaining material available at supplier will be delivered next week.
178127 | 29.10.2021 | Wall hung WC | Bulk order, Part material delivered, remaining material available at supplier will be delivered next week.
178128 | 29.10.2021 | Wall hung WC | Bulk order, Supplier has the material, delivery by next week
178191 | 23.11.2021 | Glass partition | Part material delivered, Work under progress
178208 | 30.11.2021 | UPVC Windows | Work under progress
178268 | 24.12.2021 | DB Board single phase | Part material received remaining material to de received . no stock at ssllp .
178302 | 07.01.2022 | UPVC windows | Work under progress
178304 | 07.01.2022 | UPVC windows | Work under progress
178311 | 11.01.2022 | UPVC sliding windows | Work under progress
178312 | 11.01.2022 | Glass partition | Work under progress
178317 | 12.01.2022 | UPVC sliding windows | Work under progress
178361 | 02.02.2022 | UPVC windows | Work under progress
178381 | 10.02.2022 | Inwall tank | Deliverd
178396 | 21.02.2022 | Kitchenunit | Delivery in next week .
178397 | 2022-02-21 | Sliding windows | Work under progress
178428 | 14.03.2022 | Plywood | Pick up from Sri sai rohit marketing
178430 | 15.03.2022 | CP Jali | Co ordinate with supplier for delivery
178440 | 2022-03-21 | Grills | Deliverd
178442 | 2022-03-11 | Tiles | Pick up from SSLLP-GMR
178452 | 2022-03-25 | Sliding windows | Work under process
178455 | 2022-03-26 | Creche equipments | Co ordinate with supplier for delivery
178456 | 2022-03-26 | Creche equipments | Co ordinate with supplier for delivery
178457 | 2022-03-26 | First aid kit | Co ordinate with supplier for delivery
178465 | 2022-03-29 | Notice board | Work under process
178467 | 2022-03-29 | Recreation room material | Co ordinate with supplier for delivery
178468 | 2022-03-29 | Playground area equipment | Co ordinate with supplier for delivery
178473 | 2022-03-29 | Mirror with frame | Delivered
178477 | 2022-03-31 | Toughned glass | Delivered
178478 | 2022-04-05 | Sliding windows | Work under process
178479 | 2022-04-05 | Grills | Delivered
178493 | 2022-04-08 | Regal beige, crema marfil | Pick up from GMR
178494 | 2022-04-08 | Ultra sprinkle LT | Awaiting to receive from Supplier
178508 | 2022-04-16 | Regal beige, crema marfil | pick up from GMR
178509 | 2022-04-16 | Ultra sprinkle DK | Awaiting to receive from Supplier
178514 | 2022-04-18 | Kitchenunit | Co ordinate with supplier for delivery
178517 | 2022-04-21 | Sirraco exaust fans | Deliverd
178518 | 2022-04-23 | Name plate club house | Deliverd
178522 | 2022-04-23 | Crema marfil, regal beige | Awaiting to receive from Supplier
178523 | 2022-04-23 | Luna, malashiyan, ultra tiles | Pick up from GMR