## KNM
Prepared by: | Kavitha
Report Date | 2022-06-05
Site | AGH
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
165597 | 19-03-2022 | Banquet table with ss atand + granite | Po issued- 86959, 87572
165600 | 19-03-2022 | First Aid room items | Po to be issued
165625 | 16-04-2022 | Off white plated blinds | Quotes to be recieve
165601 | 19-03-2022 | Gym items | Po issued- 86922, 87573
165606 | 19-03-2022 | Wall Fans | Po issued- 86703, 86709
165607 | 19-03-2022 | Toilet items | Po issued- 86743, 87608
165625 | 16-04-2022 | CP items for clubhouse | Wrong req.no mentioned
165663 | 25-04-2022
List of requisitions Where PO/WO is prepared and items have not received at site
Follow up with suppleir
165599 | 19-03-2022 | Crech items | 10% deliverd, remaining to be deliver by Next week delivery
165602 | 19-03-2022 | Recreation items | Next week delivery
165604 | 19-03-2022 | Playground Eqipment | Next week delivery
165609 | 19-03-2022 | AC and windows blinds | 20% delivered, remaining to be delivered by next week
165613 | 25-03-2022 | MS Gate with material | Next week delivery
16514 | 29-03-2022 | Sadarali granite top | Next week delivery
165615 | 29-03-2022 | 4x2 floor tiles | Next week delivery
165616 | 31-03-2022 | 4x2 floor tiles | Next week delivery
165622 | 2022-04-16 | electrical switches | Next week delivery
165626 | 18-04-2022 | carpet grass | Next week delivery
165629 | 23-04-2022 | Window grills | Next week delivery
165631 | 23-04-2022 | 2 x 2 Window grills | Next week delivery
165634 | 26-04-2022 | 1/18 yellow wires | Next week delivery
165635 | 26-04-2022 | Switches | Next week delivery