## GVRC
Prepared by: |  | P.Prabhakar
Report Date |  | 2022-04-30
Site |  | GVRC
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
164734 | 2022-03-16 | Scrubbing wheels | Locally purchase deliverd to site close this requisition
164791 | 2022-03-31 | 4 core alu armourd cable | PO on hold
164811 | 2022-04-07 | MS Pipe C Class | PO 87175, 87188
164812 | 2022-04-07 | Rubber matt | Enquiry in market
164820 | 2022-04-07 | Welded mesh | PO to be issue
164821 | 2022-04-07 | Castrol diesel pipe | Local purchase, remove from this list
164824 | 2022-04-09 | GI Cable trays | PO 87396
164828 | 2022-04-09 | SR 505, Gum class cloth, black tapes | PO 87967
164934 | 2022-04-11 | Vaccume deseassr, Cover | Cancelled by MD
164835 | 2022-04-12 | Safety material | PO 87539, 87540
164836 | 2022-04-12 | Aluminium cladding | PO to be issue
164834 | 2022-04-11 | Vaccume deseassr, Cover | PO to be issue
164837 | 2022-04-12 | Chainal clamp and u clamp | PO 87483
164851 | 2022-04-14 | Bathroom door | PO to be issue
164858 | 2022-04-16 | Lettan mirror | Ikea purchase, no stock with Ikea
164859 | 2022-04-16 | Lightning arresdtor | PO to be issue
164862 | 2022-04-16 | GI flat patti, insulator for GI | PO to be issue
164871 | 2022-04-19 | B class pipe | Enquiry in market
164873 | 2022-04-20 | Level float | PO 87681
164880 | 2022-04-20 | Toughned glass | PO to be issue
164882 | 2022-04-21 | Cannon camera | No avialable in market and online
164884 | 2022-04-22 | Multi function meter | Enquiry in market
164886 | 2022-04-22 | MCCB, Wire bundle | Cancelled by MD
164888 | 2022-04-23 | Lithium battary | Local purchase, remove from this list
164889 | 2022-04-23 | Biometric battary | Local purchase, remove from this list
164891 | 2022-04-23 | Aerocon pannel | Quotes to be receive
164893 | 2022-04-23 | MS Square pipe | Enquiry in market
164894 | 2022-04-23 | FRD Doors | Quotes to be receive
164896 | 2022-04-25 | Table with low storage | PO to be issue
164897 | 2022-04-25 | ETP/STP Material | PO to be issue
164899 | 2022-04-26 | Industrail salt | Locally purchased remove from this list
164900 | 2022-04-26 | Wrapping bundle | PO 87963
3
List of requisitions Where PO/WO is prepared and items have not received at site
163704 | 2021-08-07 | ACP cladding | Work under progress
164644 | 2022-02-22 | Greenlam sturdo classique versitlile | Co ordinate with Leela krishna granite supplier fro delivery
164695 | 2022-03-09 | White colour reflector | No stock with supplier
164736 | 2022-03-16 | AC Electric voltage power dector | Co ordinate with Leela krishna granite supplier fro delivery
164788 | 2022-03-30 | steel sign board | Co ordinate with Leela krishna granite supplier fro delivery
164815 | 2022-04-07 | Flame proof lights | Co ordinate with Leela krishna granite supplier fro delivery
164829 | 2022-04-09 | cera board | Co ordinate with Leela krishna granite supplier fro delivery
164857 | 2022-04-15 | ACC Wall pop work | Work under progress
164866 | 2022-04-16 | Vision clip | Work under progress
164868 | 2022-04-20 | gi White colour sheet | Co ordinate with Leela krishna granite supplier fro delivery
164869 | 2022-04-18 | RMC | Work under progress
164879 | 2022-04-20 | Panel door | Co ordinate with Leela krishna granite supplier fro delivery
164885 | 2022-04-22 | MS Square pip | Co ordinate with Leela krishna granite supplier fro delivery
164887 | 2022-04-20 | gi Pipe | Co ordinate with Leela krishna granite supplier fro delivery