## Anx - A - Attendance details
Annexure - A - Send Weekly
Details of labour charges
Name of contractor: |  | B. Anand
Company name: |  | Homeline Infra
Project name: |  | GHT
Date: |  | 2022-04-21
Period |  | From: | 2022-04-14 | To: | 2022-04-21
Sl. No. | Work Type | Worker Type | Quantity | Rate | Amount
1 | Civil work | Mason | 120 | 700 | 84000
2 | Civil work | Male helper | 70 | 550 | 38500
3 | Civil work | Female helper | 50 | 500 | 25000
4 | RCC work | Mason | 30 | 700 | 21000
5 | RCC work | Male helper | 20 | 550 | 11000
6 | RCC work | Female helper |  | 300 | 0
7 | Earth work | Mason |  | 450 | 0
8 | Earth work | Male helper | 35 | 550 | 19250
9 | Earth work | Female helper | 18 | 500 | 9000
10 | Electrician | Mason |  | 550 | 0
11 | Electrician | Male helper | 0 | 450 | 0
12 | Concreting | Male labor |  | 450 | 0
13 |  | Female helper |  | 400 | 0
14 |  |  |  |  | 0
15
16
| Total |  |  |  | 207750
Payment recommended by project manager:
Payment approved by MD:
| Prepared by: |  | Approved by: |  | MDs approval
Name | A Suresh
Sign
Date | 2022-04-21
Note:
1. Attach attendance summary from database
2. Recoomend payment as per our guideline rates for wages.

## Anx - B - Hire charges
Annexure - B - Send Weekly
Details of hire charges
Name of contractor: |  | B. Anand
Company name: |  | Homeline Infra
Project name: |  | GHT
Date: |  | 2022-04-21
Period |  | From: | 2022-04-14 | To: | 2022-04-21
Sl. No. | Equipment Type | Quantity | Rate | Units | Amount
1 | Tippers |  | 3000 | Hour | 0
2 | tractor | 3 | 1800 | Perday | 5400
3 | Hitachi |  | 1900 | Hour | 0
4 | JCB |  | 800 | Hour | 0
5 | Miller mixture |  | 18000 | per day | 0
6 | Braker | 7 | 600 | Day | 4200
7 |  |  |  |  | 0
8 |  |  |  |  | 0
9 |  |  |  |  | 0
10 |  |  |  |  | 0
11 |  |  |  |  | 0
12 |  |  |  |  | 0
13 |  |  |  |  | 0
14 |  |  |  |  | 0
15 |  |  |  |  | 0
16 |  |  |  |  | 0
17 |  |  |  |  | 0
18 |  |  |  |  | 0
19 |  |  |  |  | 0
20 |  |  |  |  | 0
21 |  |  |  |  | 0
22 |  |  |  |  | 0
23 |  |  |  |  | 0
24 |  |  |  |  | 0
25 |  |  |  |  | 0
| Total |  |  |  | 9600
Payment recommended by project manager:
Payment approved by MD:
| Prepared by: |  | Approved by: |  | MDs approval
Name | A Suresh
Sign
Date | 2022-04-21
Note:
1. Attach hirecharges summary from database
2. Recoomend payment as per our guideline rates for hirecharges.

## Anx - C - Material received
Annexure - C - send weekly
Details of magterial received
Name of contractor: |  | B. Anand
Company name: |  | Homeline Infra
Project name: |  | GHT
Date: |  | 2022-04-21
Period |  | From | 2022-04-14 | To: | 2022-04-21
Sl. No. | Material type | Received date | inward no | Quantity | Units | Rate | Amount
1 | Solid Bricks ( 6 x 8 x 12 ) | 2022-04-14 | 1803 | 450 | Nos | 25 | 11250
3 | Solid Bricks ( 6 x 8 x 12 ) | 2022-04-16 | 1804 | 450 | Nos | 25 | 11250
4 | Steel | 2022-04-18 | 1805 | 42250 | Kgs | 67.93 | 2870042.5
5 | Solid Bricks ( 6 x 8 x 12 ) | 2022-04-19 | 1806 | 450 | Nos | 25 | 11250
6 | Robo Sand | 2022-04-15 | 345 | 600 |  | 25 | 15000
7 | [6 empty] | 0
8 | [6 empty] | 0
9
10
11
12
13
14
15 | [6 empty] | 0
0
| Payment recommended by project manager: | [5 empty] | 0
| Payment approved by MD: | [5 empty] | 0
| Prepared by: |  |  | Approved by: |  | MDs approval | 2918792.5
Name | A Suresh
Sign
Date | 2022-04-21
Note:
1. Attach inward summary report from database.
2. Attach details sheet from database with photographs
3. Recoomend payment as per our guideline rates for building material.
4. Other material rates can be adopted as per bills produced.

## Anx - D - Milestone report
Annexure - D - send weekly
Mile stone report for CR.
Name of contractor: |  |  |  | B. Anand
Company name: |  |  |  | Homeline Infra
Project name: |  |  |  | GHT
Date: |  |  |  | 2020-04-30
S No | Villa no. | Type (2, 3, 4BHK) | SBUA | Work start date | Completion of plinth | Completion of RCC | Completion of brickwork and plastering | Completion of stage I | Completion of stage II | Completion of stage III | Completion of stage IV | Date of physical posession

## Anx - E1 -Estimate of work done
Annexure - E1 - Details of partial work done and not yet billed - send on the last Saturday of the month.
Estimate of work done
Name of contractor: |  |  |  | B. Anand
Company name: |  |  |  | Homeline Infra
Project name: |  |  |  | GHT
Date: |  |  |  | 2020-04-30
Note: | Enter value beween 1&100 as approximate pecentage of work completed. Enter 0 where work is completed and billed.
|  | Rate |  |  | 20 | 25 | 25 | 20 | 10 | 100
S No | Villa no. | Type (2, 3, 4BHK) | SBUA | Work start date | Earth work, footing, plinth, column1 | RRC, slabs + head room | Brick work, compound wall & site levelling | 2 coats plastering | Final finishing and handover | Total percentage of work done | Rate per sft | Construction contract value | Value of work done
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
0
|  | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0

## Anx - E2 - work done & billed
Annexure - E2 - work completed and bill raised -send on the last Saturday of the month.
Estimate of work done
Name of contractor: |  |  |  | B. Anand
Company name: |  |  |  | Homeline Infra
Project name: |  |  |  | GHT
Date: |  |  |  | 2020-04-30
Note: | Enter vlaue 1 if work is completed and billed. Enter 0 otherwise. This statement must match billing database.
|  | Rate |  |  | 20 | 25 | 25 | 20 | 10 | 100 |  |  | 0
S No | Villa no. | Type (2, 3, 4BHK) | SBUA | Work start date | Earth work, footing, plinth, column1 | RRC, slabs + head room | Brick work, compound wall & site levelling | 2 coats plastering | Final finishing and handover | Total percentage of work done | Rate per sft | GST | Construction contract value | Value of work done | Advance Paid | Advance adjusted
[12 empty] | 18 | 0 | 0 |  | 0
[12 empty] | 18 | 0 | 0 |  | 0
[13 empty] | 0 | 0 |  | 0
[13 empty] | 0 | 0 |  | 0
[13 empty] | 0 | 0 |  | 0
[13 empty] | 0 | 0 |  | 0
[13 empty] | 0 | 0 |  | 0
[13 empty] | 0 | 0 |  | 0
[13 empty] | 0 | 0 |  | 0
[13 empty] | 0 | 0 |  | 0
[13 empty] | 0 | 0 |  | 0
[13 empty] | 0 | 0 |  | 0
[13 empty] | 0 | 0 |  | 0
[13 empty] | 0 | 0 |  | 0
[13 empty] | 0 | 0 |  | 0
0
|  | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0

## Anx - F -Summary of accounts
Annexure - F - Summary of accounts -send on the last Saturday of the month.
Estimate of work done
Name of contractor: |  | B. Anand
Company name: |  | Homeline Infra
Project name: |  | GHT
Date: |  | 2020-04-30
S No | Summary - of credits | Amount
1 | Work completed & billed | 0
2 | Unbilled anount | 0
3 | Mobilization advance paid | 0
4 | Payment for increase in rate form ___ to ____
5 | Payment for increase in rate form ___ to ____
6 | Other credits
7 | Club house - billed value
8 | Club house - unbilled value - approx.
9
10
| Total A | 0
S No | Summary - of debits | Amount
1 | Amount paid | 9466620
2 | Mobilization advance adjusted | 0
3 | Other debits
4
5
6
7
8
9
10
| Total B | 9466620
| Net payable to contractor (A-B) | -9466620