## Vista
Prepared by: | vanajakshi
Report Date | 25.04.2022
Site | Serene Farms
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
150635 | 21.04.2022 | Curtain rods | Requistion sent to MD'S approval
150634 | 21.04.2022 | Curtains | Po to be issue
150629 | 11.04.2022 | Submersible pump | Estimation sent to MD'S approval
List of requisitions Where PO/WO is prepared and items have not received at site