## VOC LLP
Prepared by: | Mounika
Report Date | 09.05.22
Site | Nxetopolis
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
186263 | 04.04.22 | Deisel cans | Local Purchase
186260 | 03.03.22 | Biometric battery | Online purchase
186231 | 29.03.22 | Octagonal poles | Po to be issue
186293 | 20.04.22 | Wifi router | Online purchase
List of requisitions Where PO/WO is prepared and items have not received at site
186288 | 19.04.22 | HDPE rope | Pick from Supplier
186280 | 18.04.22 | MS Round pipe | Pick from Supplier
186279 | 18.04.22 | Safety nets | Pick from SSLLP
186277 | 16.04.22 | Armour cable | Pick from Supplier
186298 | 22.04.22 | Pen drive | Pick from Supplier