## Sheet1
Prepared by: |  | P.Prabhakar
Report Date |  | 2022-05-14
Site |  | MPL
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
178314 | 2022-01-11 | SS Railing | Cancell this requisition and raise the new requisition
178469 | 2022-03-29 | Coffee machine | On rental basis follow uo with Vyshnavi enterprises
178470 | 2022-03-29 | Sofaset | Po to be issue
178471 | 2022-03-29 | Party speaker | Online purchase
178472 | 2022-03-29 | Paper dispenser | PO 88336
178544 | 2022-05-04 | Vinyl flooring | PO to be issue
List of requisitions where PO/WO is prepared and items have not been received at site beyond the lead time:
177487 | 18.03.2021 | MCBs,modular plate ,socket | Bulk order, Part material delivered, remaining material available at supplier will be delivered next week.
177488 | 18.03.2021 | MCBs,modular plate ,socket | Bulk order, Part material delivered, remaining material available at supplier will be delivered next week.
177498 | 19.03.2021 | Stainless steel sink | Bulk order, Part material delivered, remaining material available at supplier will be delivered next week.
178122 | 26.10.2021 | UPVC Windows | Work under progress
178125 | 29.10.2021 | Wall mixtures | Bulk order, Part material delivered, remaining material available at supplier will be delivered next week.
178126 | 29.10.2021 | Wall mixtures | Bulk order, Part material delivered, remaining material available at supplier will be delivered next week.
178127 | 29.10.2021 | Wall hung WC | Bulk order, Part material delivered, remaining material available at supplier will be delivered next week.
178128 | 29.10.2021 | Wall hung WC | Bulk order, Supplier has the material, delivery by next week
178191 | 23.11.2021 | Glass partition | Part material delivered, Work under progress
178208 | 30.11.2021 | UPVC Windows | Work under progress
178268 | 24.12.2021 | DB Board single phase | Part material received remaining material to de received . no stock at ssllp .
178302 | 07.01.2022 | UPVC windows | Work under progress
178304 | 07.01.2022 | UPVC windows | Work under progress
178311 | 11.01.2022 | UPVC sliding windows | Work under progress
178312 | 11.01.2022 | Glass partition | Work under progress
178317 | 12.01.2022 | UPVC sliding windows | Work under progress
178361 | 02.02.2022 | UPVC windows | Work under progress
178397 | 2022-02-21 | Sliding windows | Work under progress
178428 | 14.03.2022 | Plywood | Pick up from Sri sai rohit marketing
178440 | 2022-03-21 | Grills | Deliverd
178452 | 2022-03-25 | Sliding windows | Work under process
178455 | 2022-03-26 | Creche equipments | Co ordinate with supplier for delivery
178456 | 2022-03-26 | Creche equipments | Co ordinate with supplier for delivery
178465 | 2022-03-29 | Notice board | Work under process
178477 | 2022-03-31 | Toughned glass | Delivered
178478 | 2022-04-05 | Sliding windows | Work under process
178479 | 2022-04-05 | Grills | Delivered
178493 | 2022-04-08 | Regal beige, crema marfil | Pick up from GMR
178494 | 2022-04-08 | Ultra sprinkle LT | Awaiting to receive from Supplier
178509 | 2022-04-16 | Ultra sprinkle DK | Awaiting to receive from Supplier
178514 | 2022-04-18 | Kitchenunit | Co ordinate with supplier for delivery
178518 | 2022-04-23 | Name plate club house | Deliverd
178522 | 2022-04-23 | Crema marfil, regal beige | Awaiting to receive from Supplier
178523 | 2022-04-23 | Luna, malashiyan, ultra tiles | Pick up from GMR
178480 | 2022-04-05 | Sliding windows | Work under process
178481 | 2022-04-05 | Grills | Work under process
178510 | 2022-04-16 | Ultra sprinkle | Pick up from SSLLP-GMR
178512 | 2022-04-16 | Glass partition | Work under process
178529 | 2022-04-28 | Roots multiclean machine | Co ordinate with supplier for delivery
178535 | 2022-04-30 | Name plates | Co ordinate with supplier for delivery
178536 | 2022-05-02 | Rain water filter plant | Work under process
178537 | 2022-05-02 | Sewage water filtration plant | Work under process
178540 | 2022-05-02 | LED Lights | Pick up from SSLLP.
178545 | 2022-05-05 | French windows | Work under process
178546 | 2022-04-06 | Sensor urinals | Co ordinate with supplier for delivery