## Vista
Prepared by: | Ramya
Report Date | 2022-21-05
Site | MHPLSOV
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
185181 | 16-04-22 | Godrej deadlock & door handles | Local purchase
List of requisitions Where PO/WO is prepared and items have not received at site
185179 | 13-04-22 | Cement solid blocks | Follow up with supplier
185184 | 19-04-22 | CPVC material | Pick from SSLLP
185188 | 21-04-22 | plumbing material | Pick from SSLLP
185189 | 22-0422 | MS box | Follow up with supplier
185190 | 25-04-22 | RCC hume pipe | Follow up with supplier
185192 | 2022-02-05 | Electrical wires | Pick from SSLLP
185193 | 2022-02-05 | Electrical wires | Pick from SSLLP