## Vista
Prepared by: | Ramya
Report Date | 2022-21-05
Site | SOV
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
184056 | 30-03-2022 | Pad locks | Po issued-Po no-86908, 86914
184080 | 2022-11-04 | Magyfying glass | Local Purchase by site
184096 | 18-04-2022 | Electrical wires | Cancelled
184106 | 22-04-2022 | Electrical wires | Po issued-Po no-87922
184118 | 26-04-2022 | Priter catrage | Work completed
184122 | 27-04-2022 | UPVC Windows | Po issued-Po no-88188
184123 | 27-04-2022 | UPVC Windows | Po issued-Po no-8819
184124 | 27-04-2022 | UPVC Windows | Po issued-Po no-88185
List of requisitions Where PO/WO is prepared and items have not received at site
184034 | 21-03-2022 | Panel doors | Pick up from SSLLP
184038 | 24-03-2022 | UPVC Windows | Follow up with supplier
184039 | 24-03-2022 | UPVC Windows | Follow up with supplier
184058 | 30-03-2022 | UPVC Windows | Follow up with supplier
184061 | 2022-01-04 | Panel doors | Pick up from SSLLP
184062 | 2022-06-04 | pendrive | Online purchase
184069 | 2022-11-04 | UPVC Windows | Follow up with supplier
184081 | 2022-12-04 | Electrical DB box | Pick up from SSLLP
184086 | 18-04-2022 | Crema marfil | pick up from GMR
184090 | 19-04-2022 | Pvc pipe | Pick up from SSLLP
184097 | 20-04-2022 | Crema marfil | pick up from GMR
184099 | 20-04-2022 | Kitchen dadoo | pick up from GMR
184100 | 20-04-2022 | tandoor stone | Follow up with supplier
184102 | 22-04-2022 | bathroom tiles | pick up from GMR
184103 | 22-04-2022 | Panel doors | Pick up from SSLLP
184107 | 22-04-2022 | UPVC Windows | Follow up with supplier
184108 | 22-04-2022 | UPVC Windows | Follow up with supplier
184109 | 23-04-2022 | internet cable | Pick up from SSLLP
184110 | 23-04-2022 | Pvc pipe | Pick up from SSLLP
184114 | 25-04-2022 | Shera board | Follow up with supplier
184117 | 26-04-2022 | A4 size paper | Pick up from SSLLP
184119 | 27-04-2022 | plumbing matrrial | Pick up from SSLLP
184126 | 27-04-2022 | CPVC Pipe works | Pick up from SSLLP
184127 | 27-04-02 | CPVC Pipe works | Pick up from SSLLP
184129 | 27-04-2022 | CP-Pillar cock | Pick up from SSLLP
184130 | 27-04-2022 | coffee powder | Follow up with supplier
184132 | 28-04-2022 | Electrical wires | Pick up from SSLLP
184134 | 2022-02-05 | bathroom tiles | pick up from GMR
184135 | 2022-02-05 | tan brown granite | Follow up with supplier
184136 | 2022-02-05 | tan brown granite | Follow up with supplier
184137 | 2022-02-05 | tan brown granite | Follow up with supplier
184138 | 2022-02-05 | tan brown granite | Follow up with supplier
184139 | 2022-02-05 | tan brown granite | Follow up with supplier
184140 | 2022-02-05 | concealed flush tanks | Pick up from SSLLP
184143 | 2022-02-05 | Eco drain pipe | Pick up from SSLLP
184144 | 2022-02-05 | Eco drain pipe | Pick up from SSLLP
184145 | 2022-02-05 | Pvc pipe | Pick up from SSLLP
184146 | 2022-02-05 | Pvc pipe | Pick up from SSLLP
184147 | 2022-02-05 | CPVC Pipe works | Pick up from SSLLP
184148 | 2022-02-05 | CPVC Pipe works | Pick up from SSLLP
184149 | 2022-04-05 | Tiles | Pick up from SSLLP
184150 | 2022-04-05 | bathroom tiles | pick up from GMR
184151 | 2022-04-05 | consumables | Pick up from SSLLP
184152 | 2020-04-02 | stationery | Pick up from SSLLP