## GVRC
Prepared by: |  | P.Prabhakar
Report Date |  | 2022-05-14
Site |  | GVRC
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
164736 | 2022-04-07 | LEd Light contact tester | Cancell this req and send new one
164812 | 2022-04-07 | Rubber mat | PO 88452
164811 | 2022-04-07 | MS C Class pipe | PO 87175, 87178
163820 | 2022-04-07 | Welded mesh | PO to be issue
164824 | 2022-04-09 | GI Cable tray | Cancelled another po issued remove from this list
164835 | 2022-04-12 | Safety material | PO 87539,87540
164836 | 2022-04-12 | Aluminium cladding | PO to be issue
164858 | 2022-04-16 | Letten mirror | No stock in IKEA
164862 | 2022-04-16 | GI Flat patti | PO to be issue
164871 | 2022-04-19 | B class pipe | PO to be issue
164873 | 2022-04-20 | Level flaot | PO 87681
164880 | 2022-04-20 | Toughned glass | PO to be issue
164882 | 2022-04-21 | Cannon camera | Material deliverd remove from list
164884 | 2022-04-22 | Multifunction meter | Cancelled by MD
164888 | 2022-04-23 | Lithium battary | Purchase locally- remove from this list
164889 | 2022-04-23 | Biometric charger | Local purchase
164893 | 2022-04-23 | Hinges | PO 88047
164898 | 2022-04-24 | Black bitumen tape | PO to be issue
164903 | 2022-04-26 | Drill bits | Req not found send it again
164912 | 2022-04-30 | CI Covers | Cancelled by MD
164914 | 2022-05-02 | Tissue dispenser | PO to be issue
164915 | 2022-05-04 | Lightning arrestor light | Online ordered awaiting to receive
164917 | 2022-05-04 | RMC | Material delivered close this requisition
164923 | 2022-05-05 | Luminious invetrer | PO 88353
164941 | 2022-05-10 | Persnol computer | Sent to sunil for his approval
164942 | 2022-05-11 | BT Patching material | PO 88305
164944 | 2022-05-11 | Surface lights | Specofocations not correct send again with correct specification
164946 | 2022-05-11 | RMC | PO 88272
164947 | 2022-05-12 | Starter 3 phase | PO 88318
List of requisitions Where PO/WO is prepared and items have not received at site
163704 | 2021-08-07 | ACP cladding | Work under progress
164788 | 2022-03-30 | steel sign board | Co ordinate with Leela krishna granite supplier fro delivery
164815 | 2022-04-07 | Flame proof lights | Co ordinate with Leela krishna granite supplier fro delivery
164829 | 2022-04-09 | cera board | Co ordinate with Leela krishna granite supplier fro delivery
164828 | 2022-04-09 | SR 505 GUM | Deliverd
164834 | 2022-04-11 | Vaccum deassaer cover | to be fabricated
164851 | 2022-04-14 | Bathroom door | Co ordinate with Leela krishna granite supplier fro delivery
164866 | 2022-04-16 | Vision clip and hole plugs | Co ordinate with Leela krishna granite supplier fro delivery
164879 | 2022-04-20 | Panel doors | Co ordinate with Leela krishna granite supplier fro delivery
164891 | 2022-04-23 | Aerocon panels | Co ordinate with Leela krishna granite supplier fro delivery
164893 | 2022-04-23 | MS Patti | Co ordinate with Leela krishna granite supplier fro delivery
164894 | 2022-04-23 | FRD Doors | Co ordinate with Leela krishna granite supplier fro delivery
164897 | 2022-04-25 | ETP/STP Material | Work under progress
164905 | 2022-04-27 | Cutting blades | Co ordinate with Leela krishna granite supplier fro delivery
164908 | 2022-04-28 | Welding rods | Co ordinate with Leela krishna granite supplier fro delivery
164909 | 2022-04-28 | Tissue paper, hand dryer | Deliverd
164913 | 2022-04-30 | Asian ace | Pick up from Ganji
164916 | 2022-05-05 | Toughned glass with patch | Work under progress
164918 | 2022-05-05 | Toughned glass with patch | Work under progress
164922 | 2022-05-05 | Solinaid valve | Deliverd
164928 | 2022-05-05 | Bullet cameras | Pick up from Corlira
164920 | 2022-05-06 | ACP cladding | Work under progress