## Vista
Prepared by: | vanajakshi
Report Date | 23.05.2022
Site | Serene Farms
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
150629 | 11.04.2022 | Submersible PumP | cancelled
150638 | 12.05.2022 | Camera charger | Deliver by this week
List of requisitions Where PO/WO is prepared and items have not received at site
150638 | 12.05.2022 | Big torch lights | PO Issued ,PO NO:88249
150638 | 12.05.2022 | Torch lights | Deliver by next week