## Vista
Prepared by: | Ramya
Report Date | 2022-21-05
Site | MHPLSOV
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
185196 | 2022-06-05 | Air conditioners | Rates under negotiation
185204 | 2022-12-05 | Cement Blocks | po issued po no 88532
185207 | 17-05-22 | HT material | po issued po no 88402
List of requisitions Where PO/WO is prepared and items have not received at site
185184 | 19-04-2022 | CPVC material | deliverd
185189 | 22-04-2022 | MS box pole | deliverd
185194 | 2022-06-05 | ceilling fan | deliverd