## Vista
Prepared by: | Ramya
Report Date | 2022-05-16
Site | NGH
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
181857 | 15.02.22 | Wifi router | Choose their and send a new req
181869 | 28.02.22 | Diesel cans | Procurment team follow up
181886 | 15.03.22 | Infrared thermometer | Cancelled by MD
181938 | 04.05.22 | Split AC s | Po to be issue
181941 | 06.05.22 | Video cameras | Po to be issue
List of requisitions Where PO/WO is prepared and items have not received at site
181857 | 15.02.22 | MI video cameras | Partially deliverd Remaining will deliverd soon
181898 | 29.03.22 | Luminous sign board | po issued
181934 | 22.04.22 | Pad locks | Coordinate with supplier
181937 | 04.05.22 | Storage units | Estimate with MD
181945 | 07.05.22 | Mics | pick up from ssllp
181946 | 07.05.22 | 3 phase starter | follow up with supplier
181948 | 10.05.22 | Virtrfied tiles | collect from GMR
181949 | 10.05.22 | Bathroom tiles | collect from GMR
181950 | 10.05.22 | Spirital level | follow up with supplier