## Vista
Prepared by: | Ramya
Report Date | 2022-05-25
Site | NGH
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
181857 | 15.02.22 | Wifi router | Choose their and send a new req
181869 | 28.02.22 | Diesel cans | Procurment team follow up
181938 | 04.05.22 | Split AC s | Rate under negotiation
181941 | 06.05.22 | video cameras | po issued PO NO-88356
181961 | 18.05.22 | wooden thadaka | po issued PO NO-88496
List of requisitions Where PO/WO is prepared and items have not received at site
181857 | 15.02.22 | MI video cameras | pick up from ssllp
181937 | 29.03.22 | Storage units | follow up with supplier
181941 | 22.04.22 | UPS | follow up with purchase assisstent
181945 | 04.05.22 | Mics | pick up from ssllp
181946 | 07.05.22 | 3 phase starter | follow up with supplier
181950 | 07.05.22 | Spirit level | follow up with supplier