## KNM
Prepared by: | Kavitha
Report Date | 2022-05-09
Site | MRGV
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
95063 | 2022-02-11 | Callisto AC CTY00034 Tiles | Camcelled
95083 | 16-03-2022 | GYM room material | PO issued
95084 | 16-03-2022 | Yoga mat, digital weighing machine | Po to issued
95086 | 16-03-2022 | Cafeterial material | PO Issued
95090 | 16-03-2022 | Split AC casette AC | Rates Under Nagotiation
95091 | 16-03-2022 | Cretch toilet material | PO issued
95094 | 16-03-2022 | Low storage | PO issued
95089 | 16-03-2022 | Lawn Mover | PO Issued- PO no-86715
95122 | 2022-05-04 | Cafeterial material | PO issued
95123 | 2022-05-04 | LED Flood lights | PO issued
List of requisitions Where PO/WO is prepared and items have not received at site
Follow up with suppleir
95082 | 16-03-2022 | Cretch toilet material | Contact supplier
95085 | 16-03-2022 | Recreation Room | Contact supplier
95087 | 16-03-2022 | RO Plant | Contact supplier
95088 | 16-03-2022 | Bosch pressure cleaner | Contact supplier
95093 | 16-03-2022 | Mirror with frame | Pick up from supplier
95095 | 16-03-2022 | Floor mat | Contact supplier
95112 | 14-04-2022 | Modular kitchen' | Contact supplier
95120 | 23-04-2022 | Armoured cable | Contact supplier