## KNM
Prepared by: | Kavitha
Report Date | 23-05-2022
Site | AGH
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
165600 | 19-03-2022 | First Aid room items | po issued
165601 | 19-03-2022 | Gym items | po issued
165606 | 19-03-2022 | Wall fans | Cancelled
165625 | 16-04-2022 | Off white plated blinds | po issued
165637 | 30-04-2022 | Swimming pool brush | Quotes to receive
165640 | 30-04-2022 | 1'' x 6'' 6'' sal wood | po issued
165641 | 2022-05-04 | SS Stand for table | po issued
165643 | 2022-05-07 | Timer machine | Quotes to receive
165644 | 2022-05-09 | MS Gate valve | po issued
165645 | 2022-05-09 | MS Gate valve | po issued
165646 | 2022-05-09 | MS Gate valve | po issued
165647 | 2022-05-09 | MS Gate valve | po issued
165648 | 2022-05-09 | MS Gate valve | po issued
165649 | 2022-05-09 | MS Gate valve | Quotes to receive
165650 | 2022-05-11 | Window grills | Quotes to receive
165651 | 2022-05-11 | AL Windows | Quotes to receive
List of requisitions Where PO/WO is prepared and items have not received at site
Follow up with suppleir
165599 | 19-03-2022 | Crech items | 80% deliverd, remaining to be deliver by Next week delivery
165602 | 19-03-2022 | Recreation items | 1% deliverd, remaining to be deliver by Next week delivery
165604 | 19-03-2022 | Playground Eqipment | Next week delivery
165607 | 19-03-2022 | Bathroom ntiles | Next week delivery
165609 | 19-03-2022 | AC and windows blinds | Next week delivery
165613 | 25-03-2022 | MS Gate with material | Next week delivery
165626 | 18-04-2022 | carpet grass | Next week delivery
165629 | 23-04-2022 | Window grills | Next week delivery
165633 | 24-04-2022 | CP items for clubhouse | Next week delivery
165631 | 23-04-2022 | 2 x 2 Window grills | Next week delivery
165639 | 30-04-2022 | Panel door | Next week delivery
165642 | 2022-05-04 | SS Stand for table | Next week delivery
165653 | 14-05-2022 | Electrical wires | Next week delivery