## VOC LLP
Prepared by: | Mounika
Report Date | 14.05.22
Site | Nxetopolis
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
186263 | 04.04.22 | Deisel cans | Procurment to follow up
186260 | 03.03.22 | Biometric battery | Online purchase
186231 | 29.03.22 | Octagonal poles | Cancelled by MD
186293 | 20.04.22 | Wifi router | Online purchase
List of requisitions Where PO/WO is prepared and items have not received at site
186280 | 18.04.22 | MS Round pipe | Pick from Supplier
186277 | 16.04.22 | Armour cable | Pick from Supplier