## Vista
Prepared by: | Ramya
Report Date | 2022-05-31
Site | NGH
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
181857 | 15.02.22 | Wifi router | Cancelled old requisition send new req
181869 | 28.02.22 | Diesel cans | Cancelled old requisition send new req
181938 | 04.05.22 | Split AC s | po to be issue
181941 | 06.05.22 | video cameras | po to be issue
181963 | 19.05.22 | A1 Sliding windows | Stock not available at ssllp
List of requisitions Where PO/WO is prepared and items have not received at site
181937 | 04.05.22 | storage units | follow up with supplier
181945 | 07.05.22 | MISC | pick up from ssllp
181950 | 10.05.22 | Spirit level | pick up from ssllp
181964 | 19.05.22 | powder coated grills | follow up with purushotham sir
181965 | 20.05.22 | plant cutters | follow up with supplier
181966 | 21.05.22 | cc rings | local purchase by raghu
181975 | 25.05.22 | panel doors | pick up from ssllp