## Vista
Prepared by: | Ramya
Report Date | 2022-31-05
Site | MHPLSOV
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
185181 | 2022-16-05 | godrej deadlock for double | po issued po no 88767
185196 | 2022-12-05 | Air condition | VRN to be receiving from supplier
185212 | 17-05-22 | SS table | po issued po no 88777
List of requisitions Where PO/WO is prepared and items have not received at site
185184 | 19-04-2022 | CPVC material | pick from SSLLP
185189 | 22-04-2022 | MS box pole | Follow up with supplier
185194 | 2022-06-05 | ceilling fan | Follow up with supplier