## Vista
Prepared by: | Ramya
Report Date | 2022-31-05
Site | SOV
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered?
184194 | 21.05.22 | Eco drain pipes | Quotes to be receive
184195 | 21.05.22 | Eco drain pipes | Quotes to be receive
184196 | 21.05.22 | Electrical wires | PO issued-po no 88675
List of requisitions Where PO/WO is prepared and items have not received at site
184069 | 06.04.22 | UPVC Windows | Follow up with supplier
184086 | 12.04.22 | Urbanwood dark | pick up from GMR
184103 | 22.04.22 | panel doors | delivery by on 2 nd
184108 | 22.04.22 | UPVC Windows | Follow up with supplier
184129 | 27-04-22 | cp-pillar cock | Pick up from SSLLP
184134 | 02.05.22 | Bathroom tiles | pick up from GMR
184144 | 02.05.22 | Eco drain pipes | Follow up with supplier
184147 | 02.05.22 | cpvc bal l valve | Pick up from SSLLP
184149 | 04.05.22 | Urbanwood dark | pick up from GMR
184153 | 05.05.22 | UPVC Windows | Follow up with supplier
184154 | 05.05.22 | UPVC Windows | Follow up with supplier
184155 | 05.05.22 | UPVC Windows | Follow up with supplier
184156 | 05.05.22 | UPVC Windows | Follow up with supplier
184157 | 05.05.22 | UPVC Windows | Follow up with supplier
184169 | 13.05.22 | Carrara tiles | pick up from GMR
184170 | 13.05.22 | Bathroom tiles | pick up from GMR
184171 | 13.05.22 | Carrara tiles | pick up from GMR
184172 | 13.05.22 | UPVC Windows | Follow up with supplier
184173 | 13.05.22 | UPVC Windows | Follow up with supplier
184174 | 13.05.22 | UPVC Windows | Follow up with supplier
184183 | 17.05.22 | pvc singl socket | Pick up from SSLLP
184184 | 17.05.22 | pvc pipenfor plumbing | Pick up from SSLLP
184192 | 17.05.22 | electrical switches | Pick up from SSLLP
184197 | 25-05-22 | door frames | deliverd
184198 | 25-05-22 | door frames | deliverd
184201 | 25-05-22 | electrical metal box | Pick up from SSLLP
184202 | 25-05-22 | electrical metal box | Pick up from SSLLP