## KNM
Prepared by: | Kavitha
Report Date | 31-05-2022
Site | AGH
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
165600 | 19-03-2022 | First Aid room items | po issued
165601 | 19-03-2022 | Gym items | po issued
165606 | 19-03-2022 | Wall fans | Cancelled
165637 | 30-04-2022 | Swimming pool brush | po issued-PO no-88596
165640 | 30-04-2022 | 1'' x 6'' 6'' sal wood | Rates to be receiving from Supplier
165643 | 2022-05-07 | Timer machine | Quotes to receive
165649 | 2022-05-09 | MS Gate valve | PO to be issue
165651 | 2022-11-05 | AL windows 6x4 | No stock , Note with MD sir
1656254 | 16-05-2022 | 1ton split AC | VRN Details to be receive from supplier
Follow up with suppleir
165599 | 19-03-2022 | Crech items | 90% deliverd, remaining to be deliver by this week
165601 |  | Gym items | This week delivery
165602 | 19-03-2022 | Recreation items | 1% deliverd, remaining to be deliver by this week
165604 | 19-03-2022 | Playground Eqipment | Supplier will send by next week
165607 | 19-03-2022 | Bathroom ntiles | Tomorrow delevery
165609 | 19-03-2022 | AC and windows blinds | This week delivery
165625 | 16-04-2022 | Off white plated blinds | This week delivery
165626 | 18-04-2022 | carpet grass | Supplier will send by next week
165629 | 23-04-2022 | Window grills | Under fabrication
165631 | 23-04-2022 | 2 x 2 Window grills | Under fabrication
165639 | 30-04-2022 | Panel door | Next week deliery
165642 | 2022-05-04 | SS Stand for table | Next week deliery
165644 | 2022-09-04 | MS Gate valve | Tomorrow delevery
165645 | 2022-09-04 | MS Gate valve | Tomorrow delevery
165646 | 2022-09-04 | MS Gate valve | Tomorrow delevery
465647 | 2022-05-09 | MS Gate valve | Tomorrow delevery
165648 | 2022-05-09 | MS Gate valve | Tomorrow delevery
165650 | 2022-11-05 | Window grills | Material under fabrication
165655 | 17-05-2022 | 6Amps switches | Tomorrow delevery