## KNM
Prepared by: | Kavitha
Report Date | 31-05-2022
Site | MCMET
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
162154 | 13-05-2022 | CPVC External | PO Issued-PO no-88432
162155 | 14-05-2022 | CPVC External | PO Issued-PO no-88312
List of requisitions Where PO/WO is prepared and items have not received at site
162153 | 25-05-2022 | CPVC Brass FTA | Material ready at SSLLP, Pick up from SSLLP